## project data
Project Management Data | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7
Project Name | Task Name | Assigned to | Start Date | Days Required | End Date | Progress | Task Status
Marketing | Market Research | Alice | 2024-01-01 | 13 | 2024-01-14 | 78% | in progress
Marketing | Content Creation | Bob | 2024-01-14 | 14 | 2024-01-28 | 100% | completed
Marketing | Social Media Planning | Charlie | 2024-01-28 | 22 | 2024-02-19 | 45% | in progress
Marketing | Campaign Analysis | Daisy | 2024-02-18 | 25 | 2024-03-14 | 0% | not started
Product Dev | Prototype Development | Ethan | 2024-01-02 | 18 | 2024-01-20 | 100% | completed
Product Dev | Quality Assurance | Fiona | 2024-01-20 | 10 | 2024-01-30 | 78% | in progress
Product Dev | User Interface Design | Gabriel | 2024-02-04 | 25 | 2024-02-29 | 0% | not started
Customer Svc | Service Improvement | Hannah | 2024-02-01 | 22 | 2024-02-23 | 100% | completed
Customer Svc | Ticket Resolution | Ian | 2024-02-24 | 25 | 2024-03-20 | 100% | completed
Customer Svc | Customer Feedback | Julia | 2024-03-21 | 30 | 2024-04-20 | 0% | not started
Financial | Budget Analysis | Kevin | 2024-02-02 | 22 | 2024-02-24 | 10% | in progress
Financial | Financial Reporting | Mark | 2024-02-13 | 21 | 2024-02-09 | 78% | in progress
Financial | Investment Planning | Mark | 2024-03-19 | 25 | 2024-04-13 | 100% | completed
Research | Market Trends Analysis | Nathan | 2024-01-02 | 23 | 2024-01-25 | 50% | in progress
Research | Data Collection | Olivia | 2024-01-26 | 32 | 2024-02-27 | 0% | not started
Research | Research Paper Writing | Peter | 2024-02-28 | 27 | 2024-03-26 | 0% | not started
Development | Software Development | Quinn | 2024-01-02 | 36 | 2024-02-07 | 100% | completed
Development | Feature Enhancement | Rachel | 2024-02-08 | 34 | 2024-03-13 | 0% | not started
Development | Code Review | Sam | 2024-03-14 | 30 | 2024-04-13 | 0% | not started
Production | Manufacturing | Tim | 2024-01-03 | 47 | 2024-02-19 | 30% | in progress
Production | Quality Control | Ursula | 2024-02-17 | 27 | 2024-03-15 | 0% | not started
Production | Packaging Design | Victor | 2024-03-14 | 22 | 2024-04-05 | 0% | not started
Sales | Lead Generation | Wendy | 2024-01-03 | 60 | 2024-03-03 | 70% | in progress
Sales | Client Meetings | Xavier | 2024-01-06 | 20 | 2024-01-26 | 78% | in progress
Sales | Contract Negotiation | Yvette | 2024-02-03 | 35 | 2024-03-09 | 0% | not started
Support | Technical Support | Zoe | 2024-01-01 | 25 | 2024-01-26 | 100% | completed
Support | Bug Fixes | Aaron | 2024-01-27 | 31 | 2024-02-27 | 100% | completed
Support | Software Updates | Bella | 2024-03-02 | 22 | 2024-03-24 | 0% | not started
Operations | Process Optimization | Calvin | 2024-01-03 | 30 | 2024-02-02 | 40% | in progress
Operations | Inventory Management | Diane | 2024-02-03 | 25 | 2024-02-28 | 0% | not started
Operations | Facility Maintenance | Edward | 2024-02-29 | 20 | 2024-03-20 | 0% | not started
Consulting | Strategic Planning | Fiona | 2024-01-02 | 35 | 2024-02-06 | 60% | in progress
Consulting | Market Expansion | Gary | 2024-02-02 | 32 | 2024-03-05 | 0% | not started
Consulting | Client Advisory | Helen | 2024-03-06 | 25 | 2024-03-31 | 0% | not started
Training | Employee Training | Isaac | 2024-01-04 | 27 | 2024-01-31 | 80% | in progress
Training | Certification Programs | Jane | 2024-01-28 | 30 | 2024-02-27 | 0% | not started
Training | Skill Development | Kyle | 2024-02-28 | 22 | 2024-03-21 | 0% | not started
Events | Event Planning | Laura | 2024-01-03 | 25 | 2024-01-28 | 30% | in progress
Events | Conference Management | Mike | 2024-02-03 | 20 | 2024-02-23 | 0% | not started
Events | Sponsorship Coordinatio | n Nancy | 2024-02-24 | 35 | 2024-03-30 | 0% | not started
Logistics | Supply Chain Management | Oscar | 2024-01-03 | 25 | 2024-01-28 | 50% | in progress
Logistics | Transportation Planning | Patricia | 2024-01-29 | 30 | 2024-02-28 | 100% | completed
Logistics | Inventory Optimization | Quentin | 2024-03-29 | 20 | 2024-04-18 | 0% | not started
Engineering | Product Design | Rachel | 2024-01-02 | 25 | 2024-01-27 | 20% | in progress
Engineering | System Integration | Sam | 2024-02-02 | 22 | 2024-02-24 | 0% | not started
Engineering | Prototype Testing | Tom | 2024-02-23 | 27 | 2024-03-21 | 0% | not started

## Pivot tables
Project Name | Count of Column1 | Progress | Count of Column1 | Project name | Count of Column6
Consulting | 3 | completed | 9 | Consulting | 3
Customer Svc | 3 | in progress | 15 | Customer Svc | 3
Development | 3 | not started | 22 | Development | 3
Engineering | 3 | Task Status | 1 | Engineering | 3
Events | 3 | (blank) |  | Events | 3
Financial | 3 | Grand Total | 47 | Financial | 3
Logistics | 3 |  |  | Logistics | 3
Marketing | 4 |  |  | Marketing | 4
Operations | 3 |  |  | Operations | 3
Product Dev | 3 |  |  | Product Dev | 3
Production | 3 |  |  | Production | 3
Project Name | 1 |  |  | Project Name | 1
Research | 3 |  |  | Research | 3
Sales | 3 |  |  | Sales | 3
Support | 3 |  |  | Support | 3
Training | 3 |  |  | Training | 3
(blank) |  |  |  | (blank)
Grand Total | 47 |  |  | Grand Total | 47
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Dashboard
Project Management Dashboard
Total Task | Completed Task | In Progrress | Not started
24 | 6 | 9 | 9